## 02_03_24
Sprint | Points | Task | Status | Notes:
2024-02-03 | 1 | Application Class | Implemented | Need to be a singleton.
2024-02-03 | 1 | Setup Github | Implemented
2024-02-03 | 1 | Config Project | Started
2024-02-03 | 1 | Imgui Setup | Implemented
2024-02-03 | 1 | Setup OpenGL | Implemented
2024-02-03 | 1 | Resouce Manager |  | Must rework shader and handle image processing class.
2024-02-03 | 1 | Window Class
2024-02-03 | 1 | Timer Class
2024-02-03 | 1 | Setup Project
2024-02-03 | 2 | Intro Doc
2024-02-03 | 2 | Image Processing Class | Started | Placeholder
2024-02-03 | 1 | Text Class | Implemented
2024-02-03 | 1 | FPS Counter Class | Started
Ends | Total
2024-02-16 | 13

## 02_17_24
Sprint | Points | Task | Status | Notes:

## Remaining Tasks
Note: Each point is ~2 hours of work.
Type | Points | Task | Status | Notes:
Video Player |  | Video Player
Video Player Controls in Imgui
GUI Loads Video
Gui Loads Video (not hard coded)
Load Video
Video |  | Load Video File
Video Player PBO handles multiple sizes
Video Player PBO
Play Video
Draw Secondary Window
Show Unprocessed Video in Secondary Video
Controls |  | Save Processed Video
XML Player
XML File Loading
XML File Saving
XML Setup
Imgui Stats
Application | 1 | Application Class | Implemented | Needs to be singleton.
| 1 | Setup Github | Implemented
| 1 | Config Project
| 2 | Imgui Setup | Implemented
| 2 | Setup OpenGL | Implemented
| 2 | Resouce Manager
| 1 | Window Class
| 1 | Timer Class
Setup Project
| 3 | Intro Doc
| 1 | Text Shader
| 1 | FPS Counter Shader
Shader | 5 | Upscale Video
| 1 | Basic Shader
| 1 | Caution Shader
| 2 | Shader Class
| 1 | Sharpen Shader
| 3 | Orientation Shader
| 2 | Image Process Class |  | New Format that needs to be integrated into the resource manager.
| 1 | Low Pass Shader
| 1 | LUT Shader
| 2 | LUT Creation
| 4 | Imgui Histogram Display
Histogram Equalization Shader
CLAHE Shader
Median Shader
Contrast Equalization Shader
Histogram (CPU)
Histogram (GPU)
Convolution Mask Shader
Logger | 1 | Logger Class
| 2 | Updated all error messages to logger